## Cover Sheet
Project Name |  | F2F SQ Creation |  |  |  |  | Note: Standardized version numbering convention: Drafts – (Before approval signature) 0.# 0.#+1 0.#+2 Published – (Once there is an approval on the document) 1.0 1.# 1.#+1
Business Unit |  | Commertial Support
Project Manager |  | Mohankumar Parthasarathy
Created By |  | Muneeswaran Pandian
Created Date |  | 2016-10-07
Reviewer |  | Mohankumar Parthasarathy
Reviewed Date |  | <Reviewe date>
Approver |  | Mohankumar Parthasarathy
Approved Date |  | <approved date>
Version # |  | <Version number>
Document History |  |  | Document Classification | Internal |  | Document ID |  | SSC/IND/FOR/GEN/010
[6 empty] | Version |  | V 1.0
Version No. | Nature of modification |  |  | Effective date | Modified By |  | Approved By | Approved Date
0.1 | Initial RTM |  |  | 2016-10-07 | Muneeswaran

## RTM
Requirements Traceability Matrix
Sr. No. | ReqID | Description | ReqOwner | AssignedTo | Architecture/High Level Design | Detailed Design | Program/Code/Class/Unit/Module | Unit Test Case/Script(s) | Integration Test Case/Script(s) | System Test Case/Script(s) | UA Test Case/Script(s) | Remarks
| REQ_001 | Login Screen: The first module will be Login Screen. It should contain below fields: User Name: There should be a text field to enter the user name in the Login Screen. Password: There should be a text field to enter the password. Login: The screen should have the Login button to login the application. • There should be a login screen to login using a valid user name and password. • There should be a text field to enter the user name in the Login Screen. • There should be a text field to enter the password. Password should be a combination of alphanumeric. • The screen should have the login button to login the application. • Once the user inputs the user name and password the system should verify both the user name and password for each login. • If the entered user name and password is incorrect, then the system should prompt an alert message to verify the given input. If the entered input is valid, the user should be able to access the application. | GHADIGAONKAR Devendra | P Muneeswaran | NA | \\10.13.90.23\01_CIRA_Application_Development\Development_Projects\Projects\Major_Projects\Commercial_Revenue_Support\NREQ00000332_F2F_SQ_Creation\2.Design_and_Development\1.Design_Document\Technical_Specification_document\4.2 Login | http://10.13.44.101:81/ext.swananje/cira_f2f.git/UserController | UTC_001 |  | FTC_001 |  | Done
| REQ_002 | Master settings used to control and authentic the application elements. Admin user can customize these elements as required. • User Access • Office • Region • Request Type • Container Type • Error Type • Priority Type • Error Category • Modes • Holidays • TAT • Status Category • Status • RFI Type • Commodity User Access : Here Admin user should able to create the user credential for the users based on the user criteria by inputting the mail id’s respectively. Office : Here Admin user should able to create, delete, update the Office as a free text, which should reflect in indexer screen as a drop down box. Region : Here Admin user should able to create, delete, update the Region as a free text, which should reflect in indexer screen as a drop down box. Request Type : Here Admin user should able to create, delete, update the Request Type as a free text, which should reflect in indexer screen as a drop down box. Container Type : Here Admin user should able to create, delete, update the Container Type as a free text, which should reflect in indexer screen as a drop down box. Error Type : Here Admin user should able to create, delete, update the Error Type as a free text, which should reflect in Publish & Audit screen as a drop down box. Priority Type : Here Admin user should able to create, delete, update the Priority Type as a free text, which should reflect in Publish & Audit screen as a drop down box. Error Category : Here Admin user should able to create, delete, update the Error Category as a free text, which should reflect in Publish & Audit screen as a drop down box. Modes : Here Admin user should able to create, delete, update the Modes Type as a free text, which should reflect in Publish & Audit screen as a drop down box. Pricing Area : Here Admin user should able to create, delete, update the Pricing Area as a free text, which should reflect in Publish & Audit screen as a drop down box. Holidays : Here Admin user should able to create, delete, update the Holiday list as a calendar selection, which should reflect in TAT calculation. TAT : Here Admin user should able to create, delete, update the TAT calculation, which should reflect in Publish & Audit home screen. Status Category: Here Admin user should able to create, delete, update the Status category as a free text, which should reflect in Publish & Audit screen as a drop down box. Status: Here Admin user should able to create, delete, update the Status as a free text, which should reflect in Publish & Audit screen as a drop down box. RFI Type : Here Admin user should able to create, delete, update the RFI Type as a free text, which should reflect in Publish & Audit screen as a drop down box. | GHADIGAONKAR Devendra | P Muneeswaran |  | \\10.13.90.23\01_CIRA_Application_Development\Development_Projects\Projects\Major_Projects\Commercial_Revenue_Support\NREQ00000332_F2F_SQ_Creation\2.Design_and_Development\1.Design_Document\Technical_Specification_document\4.3 Administrations | http://10.13.44.101:81/ext.swananje/cira_f2f.git/AdminController | UTC_002,UTC_003 |  | FTC_002, FTC_003 |  | Done
| REQ_003 | Users(Indexer) refer the customer mail which received via generic mailbox to input the information in indexing process Request Received Date & Time * : • Manual US Time Zone – This date and time should able to manually select by the calendar input by indexer. Enable the copy & paste option in this input box. Request number : • Request number will be auto-generated, combination of Week/Date/Month and Request No. in the format WK<Week No>/Date/Month#three digit auto generated number. For eg. WK30/29-07#18994 201607282015001 (received date and time is 28 July 2016 at 8:15 pm) • As soon as indexer input the mail received date and time this unique request number should be generated. Customer Name * : • Name of the customer should be free text field and should be automatically captured in Capital letters only. It should able to move cursor right and left , enable edit in between. Priority *: • Priority field should be in drop down box with the options of Standard and Urgent • By default it should take the Standard option. Region * : Region option should be in drop down box with the options of below • Gulf • MWR • NER • NVOCC • SAR • WCR By default it should be in Select category Request Type *: Type of the request should be in drop down box with the options of below • New • Correction By default it should be in Select category Office * : Selection of office should be in drop down box with the options of below • Chennai 1 (AMBIT) • Chennai 2 (AKDR) • Mumbai 1 (TRILL TOWER) • Mumbai 2 (FLC TOWER) It shall be Default as "TRILL TOWER" for Mumbai 1 users. Indexed by : • Indexed by should be captured by the user login credential. • Should not be editable by the users Indexed time: • Indexed time should be auto captured basis system time. Comments : Free text field for comments, if any. Indexing List : Indexing List Button – This button should display all indexing request. Admin should have access to edit particular field like request type, region and also should able to delete particular index which by mistakenly created. | GHADIGAONKAR Devendra | P Muneeswaran |  | \\10.13.90.23\01_CIRA_Application_Development\Development_Projects\Projects\Major_Projects\Commercial_Revenue_Support\NREQ00000332_F2F_SQ_Creation\2.Design_and_Development\1.Design_Document\Technical_Specification_document\4.5 Indexing | http://10.13.44.101:81/ext.swananje/cira_f2f.git/indexingController | UTC_004,UTC_021 |  | FTC_004,FTC_058,FTC_059,FTC_060 |  | Done
| REQ_004 | After one quote request indexed in indexing screen it will create the job in publishing Queue As soon as the Publisher clicks on the “Unique key” the request must be assigned and auto saved in the name of that particular publisher and the status must be “In Process”. It should not allow another user to access the same, should get a popup. Also, the same must reflect on the dashboard. Admin should able to unlock the request as below : • Unlock from one user and create as New request • Unlock and assign the request to another user. UPF – User Process Form Screen Request Received Date & Time : • It will show the request received time which is updated by the user. SQ No *: • Free text field. User must be given an option to Add "SQ No." along with which it must be mandatory to update "SQ No." User Name : Should capture from the Login automatically and should be greyed out. Only Admin should be able to edit the same. Request Type * : It will show the type of request • New • RFI • Correction Status : Should shows the user activity status • IN PROCESS • PENDING IN • SENT TO AUDIT • SENT TO PRICER • DONE • DISREGARD For the status "In Process", "Pending In" and "Pending Out", the following fields shall not be mandatory "SQ No.", "Modes", "Pricing Area", "Shipper Name", "Address", "City", "State" and "Partner Code" 1. If there is no query then status shall be :- In Process => Sent to Audit or Done. If the user selects the status as Done in UPF it must move to “Follow-up queue” and the same must add in Daily Report => No. of Request sent to Customer. 2. If the user wants to Disregard the request then: In process => DISREGARD. If the user selects the status as DISREGARD in UPF it must move to “Completed Queue” and the same must add in Daily Report => No. of Request sent to Customer. 3. Once the User selects "Sent to Audit", "Done" or "Disregard" in the UPF it shall be mandatory for the Users to update "Total lanes" and "Modes". 4. If the user selects the status as Done in UPF it must move to “Follow-up queue” and the same must add in Daily Report => No. of Request sent to Customer. If the user selects “Sent to Audit” the record must move in Audit queue. 5. If the user selects the status as Done in UPF it must move to “Follow-up queue” and the same must add in Daily Report => No. of Request sent to Customer. Total Lanes * Should have Increase/Decrease count button to enter the numbers pertaining to total lanes Number of Inlands * Should have Increase/Decrease count button to enter the numbers pertaining to total lanes Modes * Should have the dropdown selection P-P P-D P-R D-P D-D D-R R-P R-D R-R Note: For Mode Tab - User must be given an option to add multiple lanes Region * Should show the region which is updated by the indexer • Gulf • MWR • NER • NVOCC • SAR • WCR Pricing Area * : PA1 to PA21 User must be given an option to add multiple lines. RFI Type IF there is any RFI , user should able to raise the RFI by below RFI types and descriptions. RFI Description RFI Description field should be free text. • After RFI raised the user should select the Pending In button to stop the TAT clock as soon as it is Pending In • Should start the TAT clock when it is Pending Out. Also, request must move out of LIVE Queue and move to RFI Queue. ISR Initiated As soon as User selects "Pending In" there must be an additional mandatory field apart from "RFI type" and "RFI Description" i.e. "ISR Initiated" and it must be free text. Also, the “Pending In” must be recorded in the Daily report. Shipper Name * Linked to partner code database Address * Linked to partner code database City * Linked to partner code database State * Linked to partner code database Partner Code * Linked to partner code database CORRECTION If the request type is Indexed as Correction, an Error must be marked by the USER. Below are the fields which comes under the correction activity • Error Type  Internal  External Error type should have the dropdown box as Internal & External • Error Description Error description field should have the free test field. • Root Cause Analysis RCA field should have the free text field. • Correction Correction field should have the free text field. • Corrective Action Corrective Action field should have the free text field • Preventive Action Preventive Action field should have the free text field • Proposed Completion Date Should have the calendar to select the time and date • Actual Completion Date Should have the calendar to select the time and date • Status Open Close • Error Done By Should show the all the user list as a dropdown box. Note: • If the Request type is COR then it is mandatory to update the Error field. • COR TAT is 3hrs and should comes under red category • User must mark an Error and "Error Type", "Error Description", "Root Cause Analysis", "Correction", "Corrective Action", "Preventive Action", "Proposed Completion Date" and "Actual Completion Date" must be updated • In case if in 1 Request there are multiple SQ involved, then User must be given an option to Add "SQ No." along with which it must be mandatory to update "PA", "Total Lanes" and ""No. of inlands" Admin Dashboard Admin Track is the screen used to track the activity status based on the user in Publishing and Auditing under the categorization of All Data & Live Data • ALL DATA • LIVE DATA ALL DATA "ALL DATA" should consist of all the request status. LIVE DATA "Live Data" should consist of the all the request which are "To Be Started", "In Process" and "Pending Out". This screen should contain the columns as below : • Request No • Publisher • Status • Auditor • Status • Service Type • No. of Lanes • No. of Inlands • Region Data category should have two dropdown as ALL DATA and LIVE DATA, By giving the submit button it should retrieve the data. | GHADIGAONKAR Devendra | P Muneeswaran |  | \\10.13.90.23\01_CIRA_Application_Development\Development_Projects\Projects\Major_Projects\Commercial_Revenue_Support\NREQ00000332_F2F_SQ_Creation\2.Design_and_Development\1.Design_Document\Technical_Specification_document\4.6 Publishing Queue | http://10.13.44.101:81/ext.swananje/cira_f2f.git/publishinController | UTC_005,UTC_006,UTC_007,UTC_022, UTC_023 UTC_024 |  | FTC_005,FTC_008,FTC_013,FTC_061,FTC_062,FTC_063,FTC_064,FTC_065,FTC_075 |  | Done
| REQ_005 | As soon as one quote request moved from Publishing into Audit screen it will create the job in Auditing Queue As soon as the Auditor clicks on the “Unique key” the request must be assigned and auto saved in the name of that particular auditor and the status must be “In Process”. It should not allow another user to access the same, should get a popup. Also, the same must reflect on the dashboard. Admin should able to unlock the request as below : • Unlock from one user and create as Blank • Unlock and assign the request to another user. When Admin select the Blank then the publish time shall be back to blank. APF – Audit Process Form Screen Request Received Date & Time : • It will show the request received time which is updated by the user. Account Name : Customer Name Publisher Name : Name of the user who done the publishing Request Type : • New • RFI Resolution • Correction Auditor Name : Name of the user who done the publishing Status : If there is no query then status shall be :- In Process => Sent to Pricer. If the user selects the status as DISREGARD in APF it must move to “Completed Queue” and the same must add in Daily Report => No. of Request sent to Customer. If everything is in order then the status shall be In Process => Sent to Pricer. Total Lanes * Should have Increase/Decrease count button to enter the numbers pertaining to total lanes Number of Inlands * Should have Increase/Decrease count button to enter the numbers pertaining to total lanes Modes * Should have the dropdown selection P-P P-D P-R D-P D-D D-R R-P R-D R-R Note: For Mode Tab - User must be given an option to add multiple lanes RFI Type IF there is any RFI , user should able to raise the RFI by below RFI types and descriptions. RFI Description RFI Description field should be free text. • After RFI raised the user should select the Pending In button to stop the TAT clock as soon as it is Pending In • Should start the TAT clock when it is Pending Out. Also, request must move out of LIVE Queue and move to RFI Queue. ISR Initiated As soon as user selects “Pending In” the record must move in RFI queue and there must be field to update “ISR initiated” as a free text field. Also, the “Pending In” must be recorded in the Daily report. Correction Error Type  Internal  External Error type should have the dropdown box as Internal & External • Error Description Error description field should have the free test field. • Root Cause Analysis RCA field should have the free text field. • Correction Correction field should have the free text field. • Corrective Action Corrective Action field should have the free text field • Preventive Action Preventive Action field should have the free text field • Proposed Completion Date Should have the calendar to select the time and date • Actual Completion Date Should have the calendar to select the time and date • Status Open Close • Error Done By Should show the all the user list as a dropdown box. Note: • If the Request type is COR then it is mandatory to update the Error field. • COR TAT is 3hrs and should come under red category • User must mark an Error than "Error Type", "Error Description", "Root Cause Analysis", "Correction", "Corrective Action", "Preventive Action", "Proposed Completion Date" and "Actual Completion Date" must be updated | GHADIGAONKAR Devendra | P Muneeswaran |  | \\10.13.90.23\01_CIRA_Application_Development\Development_Projects\Projects\Major_Projects\Commercial_Revenue_Support\NREQ00000332_F2F_SQ_Creation\2.Design_and_Development\1.Design_Document\Technical_Specification_document\4.9 Auditing Queue | http://10.13.44.101:81/ext.swananje/cira_f2f.git/auditingController | UTC_008, UTC_009,UTC_026,UTC_027,UTC_028, UTC_029 |  | FTC_027, FTC_028,FTC_069,,FTC_070,FTC_071,FTC_072,FTC_073,FTC_074,FTC_076 |  | Done
| REQ_006 | RFI raised from publishing queue and Auditing queue should be comes in RFI management screen • Once received reply for RFI, Indexer should go to RFI queue => Click on UPF and make it Pending Out, • Once the Indexer make the request Pending Out there must be a box to update the Reply Receive Time => As soon as the RFI is Pending Out, the request will move out of RFI Queue and will reflect in LIVE queue. • This field must have only the option of “Pending Out”. User must have a field to update “Query resolved mail received time”. Also, the “Pending out” must be recorded in the Daily report. | GHADIGAONKAR Devendra | P Muneeswaran |  | \\10.13.90.23\01_CIRA_Application_Development\Development_Projects\Projects\Major_Projects\Commercial_Revenue_Support\NREQ00000332_F2F_SQ_Creation\2.Design_and_Development\1.Design_Document\Technical_Specification_document\4.11 RFI Queue | http://10.13.44.101:81/ext.swananje/cira_f2f.git/rfiController | UTC_010,UTC_025 |  | FTC_029,FTC_067 |  | Done
| REQ_007 | Completed Queue consists of all the completed quote requests which moved from publishing and Auditing queue with all details. | GHADIGAONKAR Devendra | P Muneeswaran |  | \\10.13.90.23\01_CIRA_Application_Development\Development_Projects\Projects\Major_Projects\Commercial_Revenue_Support\NREQ00000332_F2F_SQ_Creation\2.Design_and_Development\1.Design_Document\Technical_Specification_document\4.12 Completed Queue | http://10.13.44.101:81/ext.swananje/cira_f2f.git/rfiController | UTC_011 |  | FTC_032,FTC_078,FTC_079 |  | Done
| REQ_008 | Follow up screen contains the pricer database . It enables the track of pricer chase mails (Reminder1, Remider2) status.Triggering Reminder Mail : Reminder mail must be triggered to the Respective User (Publisher) and Generic Inbox (ssc.USinsalesF2F@cma-cgm.com). Reminder 1 is next day and Reminder 2 is day after Tomorrow. Pricing Database : • Pricer Database Form should Pop-up as soon as the Final Status is updated as "SENT TO CUSTOMER". • Pricer Database form shall be linked to "Pricing Database Tab". • Should receive the notification for the Requests for which we have not received the Quote on "ssc.USinsalesF2F@cma-cgm.com" and "ssc.dghadigaonkar@cma-cgm.com" • Should receive this report by 12EST | GHADIGAONKAR Devendra | P Muneeswaran |  | \\10.13.90.23\01_CIRA_Application_Development\Development_Projects\Projects\Major_Projects\Commercial_Revenue_Support\NREQ00000332_F2F_SQ_Creation\2.Design_and_Development\1.Design_Document\Technical_Specification_document\4.13 Follow Up Queue | http://10.13.44.101:81/ext.swananje/cira_f2f.git/followUpController | UTC_012,UTC_013 |  | FTC_033 |  | Done
| REQ_009 | • In UPF we have a field, wherein User will update the Name of the Customer, Address, City, State and Partner Code. • This data will be updated by the Users who are handling the requests. • This Data must be linked to Partner Code Database. | GHADIGAONKAR Devendra | P Muneeswaran |  | \\10.13.90.23\01_CIRA_Application_Development\Development_Projects\Projects\Major_Projects\Commercial_Revenue_Support\NREQ00000332_F2F_SQ_Creation\2.Design_and_Development\1.Design_Document\Technical_Specification_document\4.15 Partner Code Database | http://10.13.44.101:81/ext.swananje/cira_f2f.git/followUpController | UTC_007 |  | FTC_033 |  | Done
| REQ_010 | Reports enable the users and admins to pull the reports by required category and required duration. Reports are categorised by • Daily • Weekly • Monthly • Customize • Productivity • RFI Log • Error • CAPA Daily Report : Publishing : • Daily report should contains the below details • Opening balance ( No of Request) • Number of new request received ( E mail) • Number of quotes offered (quote line) • Number of Inland Quote offered • Number of sent to customer • Closing Balance (No of Request) RFI: • Opening Balance (No of RFI) • Number of New RFI Raised • Number of New RFI Resolved • Number of New RFI Pending with resolution TAT Confirmity : • Number of Request Out of TAT • TAT Missed % Accuracy – YTD • Error Received from Agency (ALL ) Weekly Report : Weekly report should contains below details • Week • Number of request received • Number of request quoted • Number of lanes quoted • Number of Inlands quoted • TAT • Accuracy • Errors Monthly Report : Weekly report should contains below details • Monthly • Number of request received • Number of request quoted • Number of lanes quoted • Number of Inlands quoted • TAT • Accuracy • Errors Productivity Report : This report should contains below details. • Serial No • Name • Publish • Audit • Total Quotes • Number of working days • Publish Target • Audit Target • Publish productivity • Audit productivity • Actual Productivity • Error • Accuracy RFI Log : RFI Log should contain below details. • Serial No • Unique NO • Date Time • Customer Name • Region • Comments • Status Error Report : Error report should contain below details. • Serial no • Week • Request no • Mail received date & Time • Error Description • Error Type • Contract Done by • Contract Audit by • Corrective Action • Preventive Action CAPA Report : CAPA report should contain below details. • Serial no • Mail received date & Time • Request no • Findings/Observation Description • Root cause analysis • Correction • Corrective Action • Preventive Action • Person responsible • Proposed completion date • Actual completion date • Status | GHADIGAONKAR Devendra | P Muneeswaran |  | \\10.13.90.23\01_CIRA_Application_Development\Development_Projects\Projects\Major_Projects\Commercial_Revenue_Support\NREQ00000332_F2F_SQ_Creation\2.Design_and_Development\1.Design_Document\Technical_Specification_document\4.16 Reports | http://10.13.44.101:81/ext.swananje/cira_f2f.git/reportController | UTC_014, UTC_015,UTC_016,UTC_017, UTC_018, UTC_019, UTC_020, UTC_030, UTC_031, UTC_032, UTC_033, UTC_034, UTC_035, UTC_036, UTC_037 |  | FTC_034, FTC_035,FTC_036,FTC_037, FTC_038, FTC_039 , FTC_040, FTC_041, FTC_042,FTC_044,FTC_045,FTC_049,FTC_50,FTC_051,FTC_052,FTC_053,FTC_054,FTC_055,FTC_056,FTC_057 |  | Done

## List (hidden)
Testing Status | Defect Status | Testing By (List the Name of Testing Team) | Testing Type
Pass | Open |  | Functional
Reject | Fixed |  | Regression
Fail | Rejected |  | UAT
Deffered | On-Hold |  | Performance
Re-Test |  |  | Stress
Ad-Hoc

## Deliverable_List
List of Deliverables
| Deliverables Follow-up | This tab is designed to help you and track the production, review and validation of the major mandatory deliverables for the current phase and future ones. This will also provide an overview to QA team and top management. This tab has to be initiated and customized with QA at the beginning of your project, especially if you have several functional package.
Sr. No. | Phase | Deliverable | Delivered? | Reviewed? | Approved? | Func. Package | Storage Location | Remarks
1 |  |  | Not Started | Not Started | Not Started
2 |  |  | Not Started | Not Started | Not Started
3 |  |  | Not Started | Not Started | Not Started
4 |  |  | Not Started | N/A | N/A
5 |  |  | Not Started | Not Started | N/A
6 |  |  | Not Started | N/A | N/A
7 |  |  | Not Started | N/A | N/A
8 |  |  | Not Started | Not Started | Not Started
9 |  |  | Not Started | Not Started | Not Started
10 |  |  | Not Started | Not Started | Not Started
11 |  |  | Not Started | N/A | N/A
12 |  |  | Not Started | Not Started | Not Started
13 |  |  | Not Started | Not Started | Not Started
14 |  |  | Not Started | Not Started | Not Started
15 |  |  | Not Started | Not Started | Not Started
16 |  |  | Not Started | Not Started | Not Started
17 |  |  | Not Started | Not Started | N/A
18 |  |  | Not Started | N/A | Not Started
19 |  |  | Not Started | Not Started | Not Started
20 |  |  | Not Started | N/A | N/A
21 |  |  | Not Started | Not Started | Not Started
22 |  |  | Not Started | Not Started | Not Started
23 |  |  | Not Started | Not Started | Not Started
24 |  |  | Not Started | Not Started | Not Started
25 |  |  | Not Started | Not Started | Not Started
26 |  |  | Not Started | N/A | N/A
27 |  |  | Not Started | Not Started | Not Started
28 |  |  | Not Started | Not Started | N/A
29 |  |  | Not Started | N/A | N/A
30 |  |  | Not Started | N/A | N/A
31 |  |  | Not Started | N/A | N/A
32 |  |  | Not Started | N/A | N/A
33 |  |  | Not Started | Not Started | Not Started
34 |  |  | Not Started | N/A | Not Started
35 |  |  | Not Started | N/A | Not Started
36 |  |  | Not Started | N/A | Not Started
37 |  |  | Not Started | N/A | N/A
38 |  |  | Not Started | Not Started | Not Started
39 |  |  | Not Started | N/A | Not Started
40 |  |  | Not Started | N/A | Not Started
41 |  |  | Not Started | N/A | Not Started
42 |  |  | Not Started | N/A | Not Started
43 |  |  | Not Started | Not Started | N/A
44 |  |  | Not Started | N/A | Not Started
45 |  |  | Not Started | N/A | N/A
46 |  |  | Not Started | Not Started | Not Started
47 |  |  | Not Started | N/A | N/A
48 |  |  | Not Started | Not Started | N/A
49 |  |  | Not Started | Not Started | Not Started
50 |  |  | Not Started | Not Started | Not Started
51 |  |  | Not Started | Not Started | Not Started
52 |  |  | Not Started | Not Started | Not Started
53 |  |  | Not Started | Not Started | Not Started
54 |  |  | Not Started | Not Started | Not Started
55 |  |  | Not Started | Not Started | Not Started
56 |  |  | Not Started | Not Started | Not Started
57 |  |  | Not Started | Not Started | Not Started
58 |  |  | Not Started | Not Started | Not Started
59 |  |  | Not Started | Not Started | Not Started
60 |  |  | Not Started | Not Started | Not Started
61 |  |  | Not Started | Not Started | Not Started
62 |  |  | Not Started | Not Started | Not Started
63 |  |  | Not Started | Not Started | Not Started
64 |  |  | Not Started | Not Started | Not Started