## Cover Sheet
Project Name |  | F2F SQ Creation |  |  |  |  | Note: Standardized version numbering convention: Drafts – (Before approval signature) 0.# 0.#+1 0.#+2 Published – (Once there is an approval on the document) 1.0 1.# 1.#+1
Project ID |  | NREQ00000332
Business Unit |  | IT - Application Development
Project Manager |  | Ananthakrishnan ANBALAGAN
Created By |  | Sunil Wananje
Created Date |  | 2016-08-18
Reviewer |  | Hemanth Kumar
Reviewed Date
Approver |  | Venkatasubramanian NARASIMHAN
Approved Date
Version # |  | 1
Document History |  |  | Document Classification | Internal |  | Document ID
Version
Version No. | Nature of modification |  |  | Effective date | Modified By |  | Approved By | Approved Date
1 | Initial Baseline |  |  | 2016-08-18 | Sunil Wananje |  | Hemanth Kumar | 2016-08-26
1.1 | Enhancement |  |  | 2016-12-01 | Sunil Wananje

## List (hidden)
Testing Status | Defect Status | Testing By (List the Name of Testing Team) | Testing Type
Pass | Open |  | Functional
Reject | Fixed |  | Regression
Fail | Rejected |  | UAT
Deffered | On-Hold |  | Performance
Re-Test |  |  | Stress
Ad-Hoc

## Activity
Project Activity Plan
Activity Plan | [6 empty] | Schedule
Project Name | F2F SQ Creation
Program Manager | Ananthakrishnan ANBALAGAN
Target
STAGE | Sl.No | MILESTONE |  | Team | Resource | Planned Begin Date | Planned End Date | Revised Start Date | Revised End Date | Actual Start Date | Actual End Date | Status
01. Inititation | 1 | Kick Off | Understand the requirements to setup | Development Team, Process Team and Project Team | Sunil Wananje | 2016-08-16 | 2016-08-16
02. Requirement Analysis | 2 | Requirement Discussion | Requirement Discussion | Development Team | Sunil Wananje | 2016-08-17 | 2016-08-17
03.Process Design Stage | 3.01 | Development | Database Planning & Design and Front End logic | Development Team | Sunil Wananje | 2016-08-19 | 2016-08-19
| 3.02 | Development | Login Screen with LDAP Functionality | Development Team | Sunil Wananje | 2016-08-22 | 2016-08-22
| 3.03 | Development | Admin - TAT Info,User Access,Holiday List,Report Points,Productivity,Priority,Region,Request Type,Container Type,Office,Modes,Error Type,Status,RFI Type,Error Category | Development Team | Sunil Wananje | 2016-08-23 | 2016-08-26 | 2016-08-23 | 2016-08-30 | 2016-08-23 | 2016-08-30 | Completed
| 3.04 | Testing | Unit Testing | Developemnt Team | Sunil Wananje | 2016-08-29 | 2016-08-29 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | Completed
| 3.05 | Testing | Functionality Testing | Functional Support
| 3.06 | Development | Indexer Form (view/edit/delete only for admin) | Development Team | Sunil Wananje | 2016-08-30 | 2016-08-30 | 2016-08-31 | 2016-09-01 | 2016-08-31 | 2016-09-01 | Completed
| 3.07 | Development | Process Queue(Publish Process) | Development Team | Sunil Wananje | 2016-08-31 | 2016-09-01 | 2016-09-01 | 2016-09-02 | 2016-09-01 | 2016-09-01 | Completed
| 3.08 | Development | User Process Form(UPF) | Development Team | Sunil Wananje | 2016-09-02 | 2016-09-06 |  |  | 2016-09-02 | 2016-09-06 | Completed
| 3.09 | Development | Correction Form | Development Team | Sunil Wananje | 2016-09-07 | 2016-09-07 |  |  | 2016-09-07 | 2016-09-07 | Completed
| 3.1 | Development | Admin Dashboard listing on all data and live data with search and filters | Development Team | Sunil Wananje | 2016-09-08 | 2016-09-09 |  |  | 2016-09-08 |  | Completed
| 3.11 | Development | Auditing Queue | Development Team | Sunil Wananje | 0 | 2016-09-14 |  |  |  |  | Completed
| 3.12 | Delelopment | Audit Process Form(APF) | Development Team | Sunil Wananje | 2016-09-15 | 2016-09-15 |  |  |  |  | Completed
| 3.13 | Development | RFI Queue(Pending In and Pending Out) | Development Team | Sunil Wananje | 2016-09-16 | 2016-09-20 |  |  |  |  | Completed
| 3.14 | Development | Completed Queue | Development Team | Sunil Wananje | 2016-09-21 | 2016-09-22 |  |  |  |  | Completed
| 3.15 | Testing | Unit Testing | Developemnt Team | Sunil Wananje | 2016-09-23 | 2016-09-23 |  |  |  |  | Completed
| 3.16 | Testing | Functionality Testing | Functional Support
| 3.17 | Development | Follow Up | Development Team | Sunil Wananje | 2016-09-26 | 2016-09-28 |  |  |  |  | Completed
| 3.18 | Development | Pricing Database | Development Team | Sunil Wananje | 2016-09-29 | 2016-09-30 |  |  |  |  | Completed
| 3.19 | Development | Partner Code Database | Development Team | Sunil Wananje | 2016-10-03 | 2016-10-04 |  |  |  |  | Completed
| 3.2 | Testing | Unit Testing | Developemnt Team | Sunil Wananje | 2016-10-05 | 2016-10-05 |  |  |  |  | Completed
| 3.21 | Testing | Functionality Testing | Functional Support
| 3.22 | Development | Daily Weekly Monthly Reports | Developemnt Team | Sunil Wananje | 2016-10-06 | 2016-10-10 |  |  |  |  | Completed
| 3.23 | Development | Productivity Report | Developemnt Team | Sunil Wananje | 2016-10-12 | 2016-10-14 |  |  |  |  | Completed
| 3.24 | Development | RFI Log Report | Developemnt Team | Sunil Wananje | 2016-10-17 | 2016-10-19 |  |  |  |  | Completed
| 3.25 | Development | Error & CAPA Report | Developemnt Team | Sunil Wananje | 2016-10-20 | 2016-10-21 |  |  |  |  | Completed
| 3.26 | Testing | Unit Testing | Developemnt Team | Sunil Wananje | 2016-10-24 | 2016-10-24 |  |  |  |  | Completed
| 3.27 | Testing | Functionality Testing | Functional Support
04. Bug Fixes | 4.01 | Development | Defect Fixes | Development Team | Sunil Wananje | 2016-10-25 | 2016-10-27 |  |  |  |  | Completed

## Enhancement Plan
Project Activity Plan
Activity Plan | [6 empty] | Schedule
Project Name | F2F SQ Creation
Program Manager | Ananthakrishnan ANBALAGAN
Target
STAGE | Sl.No | MILESTONE |  | Team | Resource | Planned Begin Date | Planned End Date | Revised Start Date | Revised End Date | Actual Start Date | Actual End Date | Status
01. Inititation | 1 | Kick Off | Understand the requirements to setup | Development Team, Functional Team and Business Team | Sunil Wananje | 2016-11-30 | 2016-11-30 |  |  |  |  | Done
02. Requirement Analysis | 2 | Requirement Discussion | Requirement Discussion | Development Team | Sunil Wananje | 2016-12-01 | 2016-12-01 |  |  |  |  | Done
03.Process Design Stage | 3 | Development | Add ISR field in audit and publish process form and remove mendotory in publish process form if status is pending in | Developemnt Team | Sunil Wananje | 2016-12-02 | 2016-12-02 |  |  |  |  | Completed
| 3.1 | Development | Code Review | Developemnt Team | Kuppusamy Chandra Bose | 2016-12-02 | 2016-12-02 |  |  |  |  | Completed
| 3.2 | Development | Status syncronization as per current status in publish queue | Developemnt Team | Sunil Wananje | 2016-12-02 | 2016-12-05 |  |  |  |  | Completed
| 3.3 | Development | Code Review | Developemnt Team | Kuppusamy Chandra Bose | 2016-12-05 | 2016-12-05 |  |  |  |  | Completed
| 3.4 | Development | Status syncronization as per current status in audit queue | Developemnt Team | Sunil Wananje | 2016-12-05 | 2016-12-06 |  |  |  |  | Completed
| 3.5 | Development | Add Modes, Total Lanes, No of Inlands in audit process form | Developemnt Team | Sunil Wananje | 2016-12-06 | 2016-12-06 |  |  |  |  | Completed
| 3.6 | Development | Code Review | Developemnt Team | Kuppusamy Chandra Bose | 2016-12-07 | 2016-12-07 |  |  |  |  | Completed
| 3.7 | Development | Add Export to excel functionality to all queue i.e publish, audit,rfi,completed, all/live data, follow up, pricer database, partner code database | Developemnt Team | Sunil Wananje | 2016-12-07 | 2016-12-09 |  |  |  |  | Completed
| 3.8 | Development | Code Review | Developemnt Team | Kuppusamy Chandra Bose | 2016-12-12 | 2016-12-12
| 3.9 | Testing | Unit Testing | Developemnt Team | Sunil Wananje | 2016-12-12 | 2016-12-12
| 3.91 | Functional Testing | Functionality Testing | Functional Support | PANDIAN Muneeswaran
04. Bug Fixes | 4 | Development | Defect Fixes | Developemnt Team | Sunil Wananje | 2016-12-15 | 2016-12-16