## Cover Sheet
Project Name |  | F2F SQ Creation |  |  |  |  | Note: Standardized version numbering convention: Drafts – (Before approval signature) 0.# 0.#+1 0.#+2 Published – (Once there is an approval on the document) 1.0 1.# 1.#+1
Project ID |  | NREQ00000332
Business Unit |  | IT - Business Solutions
Project Manager |  | Mohankumar PARTHASARATHY
Created By |  | Muneeswaran & Thaslim Salaga
Created Date |  | 2016-08-18
Reviewer |  | Mohankumar PARTHASARATHY
Reviewed Date |  | 2016-10-17
Approver |  | Mohankumar PARTHASARATHY
Approved Date |  | 2016-10-17
Version # |  | 1.2
Document History |  |  | Document Classification | Internal |  | Document ID
Version
Version No. | Nature of modification |  |  | Effective date | Modified By |  | Approved By | Approved Date
1 | F2F SQ Creation |  |  | 2016-08-18 | Muneeswaran |  | Mohankumar PARTHASARATHY | 2016-08-18
1.1 | Admin module delievery date changed By Dev team |  |  | 2016-08-30 | Muneeswaran |  | Mohankumar PARTHASARATHY | 2016-08-30
1.2 | Revised date from Dev. Team |  |  | 2016-10-14 | Muneeswaran |  | Thaslim Salaga | 2016-10-17
1.3 | Enhancement |  |  | 2016-12-01 | Sunil Wananje

## List (hidden)
Testing Status | Defect Status | Testing By (List the Name of Testing Team) | Testing Type
Pass | Open |  | Functional
Reject | Fixed |  | Regression
Fail | Rejected |  | UAT
Deffered | On-Hold |  | Performance
Re-Test |  |  | Stress
Ad-Hoc

## Activity (hidden)
Project Activity Plan
Activity Plan | [6 empty] | Schedule
Project Name | F2F SQ Creation
Program Manager | Ananthakrishnan ANBALAGAN
Target
STAGE | Sl.No | MILESTONE |  | Team | Resource | Planned Begin Date | Planned End Date | Revised Start Date | Revised End Date | Actual Start Date | Actual End Date | Status
01. Inititation | 1 | Kick Off | Initial requirement discussion | Development Team, Process Team and Functional Support | PANDIAN Muneeswaran | 2016-07-26 | 2016-07-26
| 1.01 | Kick Off | Understand the requirements to setup | Development Team, Process Team and Functional Support | Hemraj Solanki | 2016-07-26 | 2016-07-27
02. Requirement Analysis | 2 | Solution Document | Solution Document KT - New Developer | Functional Support | PANDIAN Muneeswaran | 2016-08-16 | 2016-08-17
| 2.01 | Requirement Discussion | Requirement Discussion | Development Team | Sunil Wananje | 2016-08-16 | 2016-08-17
| 2.02 | Solution Document | Preparing Solution Document | Functional Support | PANDIAN Muneeswaran | 2016-08-18 | 2016-08-22
03.Process Design Stage | 3.01 | Development | Database Planning & Design and Front End logic | Development Team | Sunil Wananje | 2016-08-19 | 2016-08-19
| 3.02 | Development | Login Screen with LDAP Functionality | Development Team | Sunil Wananje | 2016-08-22 | 2016-08-22
| 3.03 | Development | Admin - TAT Info,User Access,Holiday List,Report Points,Productivity,Priority,Region,Request Type,Container Type,Office,Modes,Error Type,Status,Query Type,Error Category,RFI Type. | Development Team | Sunil Wananje | 2016-08-23 | 2016-08-26 | 2016-08-23 | 2016-08-30 | 2016-08-23 | 2016-08-30 | Completed
| 3.04 | Testcase | Creation of Testcase | Functional Support | PANDIAN Muneeswaran | 2016-08-24 | 26-Sep-16 (Fri)
| 3.05 | Testing | Unit Testing | Developemnt Team | Sunil Wananje | 2016-08-29 | 2016-08-29 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | Completed
| 3.06 | Functional Testing | Execution of Functional Test Case | Functional Support | PANDIAN Muneeswaran | 2016-08-30 | 2016-08-30 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | Completed
| 3.07 | Testing | Bug Fix - Functional Testing | Developemnt Team | Sunil Wananje | 2016-08-30 | 2016-08-30 | 2016-08-31 | 2016-09-01 | 2016-08-31 | 2016-09-01 | Completed
| 3.08 | Development | Indexer Form | Development Team | Sunil Wananje | 2016-08-30 | 2016-09-01 | 2016-09-01 | 2016-09-02 | 2016-09-01 | 2016-09-02 | Completed
| 3.09 | Development | Process Queue(Publish Process) | Development Team | Sunil Wananje | 2016-09-02 | 2016-09-07 | 2016-09-02 | 2016-09-03 | 2016-09-02 | 2016-09-03 | Completed
| 3.1 | Development | User Process Form(UPF) | Development Team | Sunil Wananje | 2016-09-07 | 2016-09-08 | 2016-09-03 | 2016-09-06 | 2016-09-03 | 2016-09-06 | Completed
| 3.11 | Development | Correction Form | Development Team | Sunil Wananje | 2016-09-09 | 2016-09-12 |  |  | 2016-09-07 | 2016-09-07 | Completed
| 3.12 | Development | Admin Dashboard listing on all data and live data with search and filters | Development Team | Sunil Wananje | 2016-09-14 | 2016-09-16 |  |  | 2016-09-08 | 2016-09-09 | Completed
| 3.13 | Development | Auditing Queue | Development Team | Sunil Wananje | 2016-09-19 | 2016-09-21 |  |  | 0 | 2016-09-14 | Completed
| 3.14 | Delelopment | Audit Process Form(APF) | Development Team | Sunil Wananje | 2016-09-22 | 2016-09-26 |  |  | 2016-09-15 | 2016-09-15 | Completed
| 3.15 | Development | RFI Queue(Pending In and Pending Out) | Development Team | Sunil Wananje | 2016-09-27 | 2016-09-29 |  |  | 2016-09-16 | 2016-09-20 | Completed
| 3.16 | Development | Completed Queue | Development Team | Sunil Wananje | 2016-09-30 | 2016-10-03 |  |  | 2016-09-21 | 2016-09-22 | Completed
| 3.17 | Testing | Unit Testing | Developemnt Team | Sunil Wananje | 2016-10-04 | 2016-10-04 |  |  | 2016-09-23 | 2016-09-23 | Completed
| 3.18 | Testing | Functionality Testing | Functional Support | PANDIAN Muneeswaran | 2016-10-05 | 2016-10-18
| 3.19 | Testing | Bug Fix - Functional Testing | Developemnt Team | Sunil Wananje | 2016-10-05 | 2016-10-18
| 3.2 | Development | Follow Up | Development Team | Sunil Wananje | 2016-10-05 | 2016-10-07
| 3.21 | Development | Pricing Database | Development Team | Sunil Wananje | 2016-10-10 | 2016-10-13
| 3.22 | Development | Partner Code Database | Development Team | Sunil Wananje | 2016-10-14 | 2016-10-18
| 3.23 | Testing | Unit Testing | Developemnt Team | Sunil Wananje | 2016-10-19 | 2016-10-19
| 3.24 | Testing | Functionality Testing | Functional Support | PANDIAN Muneeswaran | 2016-10-20 | 2016-10-24
| 3.25 | Testing | Bug Fix - Functional Testing | Developemnt Team | Sunil Wananje | 2016-10-20 | 2016-10-24
| 3.26 | Development | Daily Weekly Monthly Reports | Developemnt Team | Sunil Wananje | 2016-10-20 | 2016-10-24
| 3.27 | Development | Productivity Report | Developemnt Team | Sunil Wananje | 2016-10-25 | 2016-10-27
| 3.28 | Development | RFI Log Report | Developemnt Team | Sunil Wananje | 2016-10-28 | 2016-11-02
| 3.29 | Development | Error & CAPA Report | Developemnt Team | Sunil Wananje | 2016-11-03 | 2016-11-07
| 3.3 | Testing | Unit Testing | Developemnt Team | Sunil Wananje | 2016-11-08 | 2016-11-08
| 3.31 | Testing | Functionality Testing | Functional Support | PANDIAN Muneeswaran | 2016-11-09 | 2016-11-16
| 3.32 | Testing | Bug Fix - Functional Testing | Developemnt Team | Sunil Wananje | 2016-11-09 | 2016-11-16
04. Training | 4.01 | Training | Training Document preparation | Functional Support | PANDIAN Muneeswaran | 2016-10-25 | 2016-10-28
| 4.02 | Training | Key User Training | Functional Support | PANDIAN Muneeswaran | 2016-11-17 | 2016-11-18
05. UAT Stage | 5 | User Acceptance Testing | UAT - Testing | Business Team | Key Users | 2016-11-21 | 2016-10-25
| 5.01 | Testing | UAT - Bug Fixing | Development Team | Sunil Wananje | 2016-11-21 | 2016-11-28
| 5.02 | User Acceptance Testing | UAT - Re-Testing | Business Team | Key Users | 2016-11-29 | 2016-11-29
06. Documentation | 6.01 | Go-Live Approval | Go-Live Approval - QG | Functional Support | PANDIAN Muneeswaran | 2016-11-30 | 2016-11-30
07. Deploy and Sign off | 7 | Go-Live | Release for Production | Functional Support | PANDIAN Muneeswaran | 2016-12-01 | 2016-12-01
| 7.01 | Testing | Sanity Check on Production | Functional Support | PANDIAN Muneeswaran | 2016-12-01 | 2016-12-01
08.Post Go-Live Support | 8 | Ticket Management | Review Ticket and Route for Production | Functional Support | PANDIAN Muneeswaran | 2016-12-02 | 2016-12-06
| 8.01 | Development | Overall Defect Fixes | Development Team | Hemraj Solanki | 2016-12-02 | 2016-12-06
Note on M15: Muneeswaran P: Due to new resource allocation development

## Functionality
Project Activity Plan
Activity Plan | [6 empty] | Schedule
Project Name | F2F SQ Creation
Program Manager | Ananthakrishnan ANBALAGAN
Target
STAGE | Sl.No | MILESTONE |  | Team | Resource | Planned Begin Date | Planned End Date | Revised Start Date | Revised End Date | Actual Start Date | Actual End Date | Status
01. Inititation | 1 | Kick Off | Initial requirement discussion | Development Team, Process Team and Functional Support | PANDIAN Muneeswaran | 2016-07-26 | 2016-07-26
| 1.01 | Kick Off | Understand the requirements to setup | Development Team, Process Team and Functional Support | Sunil Wananjeraj Solanki | 2016-07-26 | 2016-07-27
02. Requirement Analysis | 2 | Solution Document | Solution Document KT - New Developer | Functional Support | PANDIAN Muneeswaran | 2016-08-16 | 2016-08-17
| 2.01 | Requirement Discussion | Requirement Discussion | Development Team | Sunil Wananje | 2016-08-16 | 2016-08-17
| 2.02 | Solution Document | Preparing Solution Document | Functional Support | PANDIAN Muneeswaran | 2016-08-18 | 2016-08-22
03.Process Design Stage | 3 | Development | Database Planning & Design and Front End logic | Development Team | Sunil Wananje | 2016-08-19 | 2016-08-19
| 3.01 | Development | Login Screen with LDAP Functionality | Development Team | Sunil Wananje | 2016-08-22 | 2016-08-22
| 3.02 | Development | Admin - TAT Info,User Access,Holiday List,Report Points,Productivity,Priority,Region,Request Type,Container Type,Office,Modes,Error Type,Status,Query Type,Error Category,RFI Type. | Development Team | Sunil Wananje | 2016-08-23 | 2016-08-26 | 2016-08-23 | 2016-08-30 | 2016-08-23 | 2016-08-30 | Completed
| 3.03 | Testcase | Creation of Testcase | Functional Support | PANDIAN Muneeswaran | 2016-08-24 | 26-Sep-16 (Fri)
| 3.04 | Testing | Unit Testing | Developemnt Team | Sunil Wananje | 2016-08-29 | 2016-08-29 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | Completed
| 3.05 | Functional Testing | Execution of Functional Test Case for 3.02 & 3.03 | Functional Support | PANDIAN Muneeswaran | 2016-08-30 | 2016-08-30 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | Completed
| 3.06 | Testing | Bug Fix - Functional Testing | Developemnt Team | Sunil Wananje | 2016-08-30 | 2016-08-30 | 2016-08-31 | 2016-09-01 | 2016-08-31 | 2016-09-01 | Completed
| 3.07 | Development | Indexer Form | Development Team | Sunil Wananje | 2016-08-30 | 2016-09-01 | 2016-09-01 | 2016-09-02 | 2016-09-01 | 2016-09-02 | Completed
| 3.08 | Development | Process Queue(Publish Process) | Development Team | Sunil Wananje | 2016-09-02 | 2016-09-07 | 2016-09-02 | 2016-09-03 | 2016-09-02 | 2016-09-03 | Completed
| 3.09 | Development | User Process Form(UPF) | Development Team | Sunil Wananje | 2016-09-07 | 2016-09-08 | 2016-09-03 | 2016-09-06 | 2016-09-03 | 2016-09-06 | Completed
| 3.1 | Development | Correction Form | Development Team | Sunil Wananje | 2016-09-09 | 2016-09-12 |  |  | 2016-09-07 | 2016-09-07 | Completed
| 3.11 | Development | Admin Dashboard listing on all data and live data with search and filters | Development Team | Sunil Wananje | 2016-09-14 | 2016-09-16 |  |  | 2016-09-08 | 2016-09-09 | Completed
| 3.12 | Development | Auditing Queue | Development Team | Sunil Wananje | 2016-09-19 | 2016-09-21 |  |  | 0 | 2016-09-14 | Completed
| 3.13 | Delelopment | Audit Process Form(APF) | Development Team | Sunil Wananje | 2016-09-22 | 2016-09-26 |  |  | 2016-09-15 | 2016-09-15 | Completed
| 3.14 | Development | RFI Queue(Pending In and Pending Out) | Development Team | Sunil Wananje | 2016-09-27 | 2016-09-29 |  |  | 2016-09-16 | 2016-09-20 | Completed
| 3.15 | Development | Completed Queue | Development Team | Sunil Wananje | 2016-09-30 | 2016-10-03 |  |  | 2016-09-21 | 2016-09-22 | Completed
| 3.16 | Testing | Unit Testing | Developemnt Team | Sunil Wananje | 2016-10-04 | 2016-10-04 |  |  | 2016-09-23 | 2016-09-23 | Completed
| 3.17 | Functional Testing | Functionality Testing | Functional Support | PANDIAN Muneeswaran | 2016-10-05 | 2016-10-18 | 2016-10-13 | 2016-10-17
| 3.18 | Functional Testing | Bug Fix - Functional Testing | Developemnt Team | Sunil Wananje | 2016-10-05 | 2016-10-18 | 2016-10-13 | 2016-10-18
| 3.19 | Development | Follow Up | Development Team | Sunil Wananje | 2016-10-05 | 2016-10-07 |  |  | 2016-09-26 | 2016-09-28 | Completed
| 3.2 | Development | Pricing Database | Development Team | Sunil Wananje | 2016-10-10 | 2016-10-13 |  |  | 2016-09-29 | 2016-09-30 | Completed
| 3.21 | Development | Partner Code Database | Development Team | Sunil Wananje | 2016-10-14 | 2016-10-18 |  |  | 2016-10-03 | 2016-10-04 | Completed
| 3.22 | Testing | Unit Testing | Developemnt Team | Sunil Wananje | 2016-10-19 | 2016-10-19 |  |  | 2016-10-05 | 2016-10-05 | Completed
| 3.23 | Functional Testing | Functionality Testing | Functional Support | PANDIAN Muneeswaran | 2016-10-20 | 2016-10-24 | 2016-10-18 | 2016-10-19
| 3.24 | Functional Testing | Bug Fix - Functional Testing | Developemnt Team | Sunil Wananje | 2016-10-20 | 2016-10-24 | 2016-10-18 | 2016-10-20
| 3.25 | Training | Training Document preparation | Functional Support | PANDIAN Muneeswaran | 2016-10-25 | 2016-10-28 | 2016-10-20 | 2016-10-20
04. Training | 3.24 | Functional Testing | Retesting - Functionality Testing | Functional Support | PANDIAN Muneeswaran | - | - | 2016-10-21 | 2016-10-21
| 4.02 | Training | Key User Training | Functional Support | PANDIAN Muneeswaran | 2016-11-01 | 2016-11-02 | 2016-10-21 | 2016-10-21
05. UAT Stage | 5 | User Acceptance Testing | UAT - Testing | Business Team | GHADIGAONKAR Devendra | 2016-11-03 | 2016-11-09 | 2016-10-24 | 2016-10-31
| 5.01 | Testing | UAT - Bug Fixing | Development Team | Sunil Wananje | 2016-11-03 | 2016-11-10 | 2016-10-24 | 2016-11-01
| 5.02 | User Acceptance Testing | UAT - Re-Testing | Business Team | GHADIGAONKAR Devendra | 2016-11-11 | 2016-11-11 | 2016-11-02 | 2016-11-03
06. Documentation | 6.01 | Go-Live Approval | Go-Live Approval - QG | Functional Support | PANDIAN Muneeswaran | 2016-11-04 | 2016-11-04 | 2016-11-03 | 2016-11-03
07. Deploy and Sign off | 7 | Go-Live | Release for Production | Functional Support | PANDIAN Muneeswaran | 2016-11-07 | 2016-11-07 | 2016-11-04 | 2016-11-04
| 7.01 | Testing | Sanity Check on Production | Functional Support | PANDIAN Muneeswaran | 2016-11-07 | 2016-11-07 | 2016-11-04 | 2016-11-04
08.Post Go-Live Support | 8 | Go-Live | Go-Live | Functional Support | PANDIAN Muneeswaran | 2016-11-08 | 2016-11-08 | 2016-11-04 | 2016-11-04
Note on M15: Muneeswaran P: Due to new resource allocation development
Note on I35: Thaslim Salaga A: Development team communicated on 11-oct
Note on I41: Thaslim Salaga A: Thaslim Salaga A: Development team communicated on 11-oct

## Reports
Project Activity Plan
Activity Plan | [6 empty] | Schedule
Project Name | F2F SQ Creation
Program Manager | Ananthakrishnan ANBALAGAN
Target
STAGE | Sl.No | MILESTONE |  | Team | Resource | Planned Begin Date | Planned End Date | Revised Start Date | Revised End Date | Actual Start Date | Actual End Date | Status
01.Process Design Stage | 3.26 | Development | Daily Weekly Monthly Reports | Developemnt Team | Sunil Wananje | 2016-10-20 | 2016-10-24 |  |  | 2016-10-19 | 2016-10-24 | Completed
| 3.27 | Development | Productivity Report | Developemnt Team | Sunil Wananje | 2016-10-25 | 2016-10-27 |  |  | 2016-10-25 | 2016-10-27 | Completed
| 3.28 | Development | RFI Log Report | Developemnt Team | Sunil Wananje | 2016-10-28 | 2016-11-02 |  |  | 2016-10-28 | 2016-11-01 | Completed
| 3.29 | Development | Error & CAPA Report | Developemnt Team | Sunil Wananje | 2016-11-03 | 2016-11-07 |  |  | 2016-11-02 | 2016-11-04 | Completed
| 3.3 | Testing | Unit Testing | Developemnt Team | Sunil Wananje | 2016-11-08 | 2016-11-08 |  |  | 2016-11-04 | 2016-11-07 | Completed
| 3.31 | Functional Testing | Functionality Testing | Functional Support | PANDIAN Muneeswaran | 2016-11-09 | 2016-11-16
| 3.32 | Functional Testing | Bug Fix - Functional Testing | Developemnt Team | Sunil Wananje | 2016-11-09 | 2016-11-17
02. Training | 4.01 | Functional Testing | Training Document preparation | Functional Support | PANDIAN Muneeswaran | 2016-11-17 | 2016-11-18
| 4.02 | Training | Key User Training | Functional Support | PANDIAN Muneeswaran | 2016-11-21 | 2016-11-21
03. UAT Stage | 5 | User Acceptance Testing | UAT - Testing | Business Team | Key Users | 2016-11-22 | 2016-11-25
| 5.01 | Testing | UAT - Bug Fixing | Development Team | Sunil Wananje | 2016-11-22 | 2016-11-28
| 5.02 | User Acceptance Testing | UAT - Re-Testing | Business Team | Key Users | 2016-11-29 | 2016-11-29
04. Documentation | 6.01 | Go-Live Approval | Go-Live Approval - QG | Functional Support | PANDIAN Muneeswaran | 2016-11-30 | 2016-11-30
05. Deploy and Sign off | 7 | Go-Live | Release for Production | Functional Support | PANDIAN Muneeswaran | 2016-12-01 | 2016-12-01
| 7.01 | Testing | Sanity Check on Production | Functional Support | PANDIAN Muneeswaran | 2016-12-01 | 2016-12-01
06.Post Go-Live Support | 8 | Go-Live | Go-Live | Functional Support | PANDIAN Muneeswaran | 2016-12-01 | 2016-12-01
4

## Enhancement
Project Activity Plan
Activity Plan | [6 empty] | Schedule
Project Name | F2F SQ Creation
Program Manager | Ananthakrishnan ANBALAGAN
Target
STAGE | Sl.No | MILESTONE |  | Team | Resource | Planned Begin Date | Planned End Date | Revised Start Date | Revised End Date | Actual Start Date | Actual End Date | Status
01.Enhancement Stage | 3.26 | Development | Add ISR field in audit and publish process form and remove mendotory in publish process form if status is pending in | Developemnt Team | Sunil Wananje | 2016-12-02 | 2016-12-02
| 3.27 | Development | Status syncronization as per current status in publis queue | Developemnt Team | Sunil Wananje | 2016-12-02 | 2016-12-05
| 3.28 | Development | Status syncronization as per current status in audit queue | Developemnt Team | Sunil Wananje | 2016-12-06 | 2016-12-06
| 3.29 | Development | Add Modes, Total Lanes, No of Inlands in audit process form | Developemnt Team | Sunil Wananje | 2016-12-07 | 2016-12-07
| 3.3 | Testing | Unit Testing | Developemnt Team | Sunil Wananje | 2016-12-08 | 2016-12-08
| 3.31 | Functional Testing | Functionality Testing | Functional Support | PANDIAN Muneeswaran
4