## Cover Sheet
Project Name |  | Guideline Quoting |  |  |  |  | Note: Standardized version numbering convention: Drafts – (Before approval signature) 0.# 0.#+1 0.#+2 Published – (Once there is an approval on the document) 1.0 1.# 1.#+1
Business Unit |  | IT - Application Development
Project Manager |  | Ananthakrishan Hemanth/Ananthakrishan
Created By |  | Hemraj Solanki
Created Date |  | 2016-09-04
Reviewer |  | Hemanth Kumar Anantha Krishnan
Reviewed Date |  | 2016-12-02
Approver |  | Venkatasubramanian NARASIMHAN
Approved Date
Version # |  | 1
Document History |  |  | Document Classification | Internal |  | Document ID |  | SSC/IND/FOR/GEN/059
[6 empty] | Version |  | V 1.1
Version No. | Nature of modification |  |  | Effective date | Modified By |  | Approved By | Approved Date
1 | Initial Draft |  |  | 2016-12-02 | Hemraj Solanki |  | Hemanth Kumar | 2016-12-02

## ReadMe
Instructions
Objective |  | This estimation calculator has been developed to help the Project team to arrive the efforts based on the approved Solution Document( Previously Known as BRD).
How to work on this estimation calculator ? |  | Step 1: You need to identify the Screens / Input fields / Upload / Search etc., and put the complexities accordingly. Once you filled complexities for entire requirements the developments efforts would be calculated. Here the benchmarks have been arrived by considering the industry standards, experience. Step 2: Based on the CUT ( Coding & Unit Testing) efforts and weightage distribution defined in "Benchmarks" sheet, the SDLC efforts are arrived in "Summary" sheet.
How to determine the Complexities for each program units or requirements ? |  | The below information is to understand about the complexities of each program units. Hence kindly go through and determine the number of complexities accordingly. If you find out certain combinations not present in the given Instructions, you can arrive the number based on multiple complexities for one program Units. For example, if you have an Input Screen with 20 input fields with complex layouts, you can determine its complexities as 2-Medium
S.No | Program Units | Comments
1 | Input Screen (IS) / Form | The IS considered as Simple when a screen has less than 3 input fields with no complex layouts and special requirements. The IS considered as Medium when a screen has more than 3 but less than 5 input fields with no complex layouts and special requirements. The IS considered as Complex when a screen has more than 5 input fields with complex layouts and special requirements. Note: This effort is for screen design with layout and the submission of data to presentation layer.
2 | Search Criteria / ( DB Query) Create, Update, Retrieve, and Delete | The search criteria is considered as Simple when the screen has less than 2 search fields and simple DB Query from 1 or 2 tables The search criteria is considered as Medium when the screen has more than 2 search fields and using DB Query from more than 2 tables but less than 6 tables The search criteria is considered as Complex when the screen has more than 6 search fields and using DB Query from more than 6 tables with complex search queries
3 | Display Screens | The display screen is considered as Simple when the screen has displayed with less than 5 output fields without any computational logic The display screen is considered as Medium when the screen has displayed with more than 10 output fields without any computational logic and also with pagination The display screen is considered as Complex when the screen has displayed with more than 10 output fields with any computational logic and also with pagination
4 | Processing Logics | The processing logic is considered as Simple when the logic has a simple mathematical and statistical computations apart from DB query retrieval. Also includes simple business validations. The processing logic is considered as Medium when the logic has more than 2 normal mathematical and statistical computations apart from DB query retrieval. Also includes business validations. The processing logic is considered as Complex when the logic has more than 2 complex mathematical and statistical computations apart from DB query retrieval . Also includes complex business validations.
5 | Batch Jobs | The batch job is considered as Simple when the batch operation is related to persistence with a feed file reading, where feed file can be in form of text or excel file. Also persistence is assumed for only 1 table. The batch job is considered as Medium when the batch operation is related to persistence with a feed file reading, where feed file can be in form of text or excel file. Here persistence is assumed for more than 2 tables, where the data is being persisted in master & detail tables. The batch job is considered as Complex when the batch operation is related to persistence with a feed file reading, where feed file can be in form of text or excel file. Here persistence is assumed for more than 3 tables with processing logics. Note: This effort includes the re-run logic and other normal batch operation logics viz., threading etc.
6 | Upload | The upload is considered as Simple when the upload of data through a file would be persisted with only 1 table. The upload is considered as Medium when the upload of data through a file would be persisted with more than 1 table with minimal computational logic. The upload is considered as Complex when the upload of data through a file would be persisted with more than 2 table with complex computational logic. Note: This effort includes the error handling while uploads
7 | Download | The download is considered as Simple when the download of data through simple query that involve equi and outer joins and without any computation logic as well as no special formatting. The download is considered as Medium when the download of data through queries that involve equi and outer joins and with simple computation logic as well as minimal / basic formatting. The download is considered as Complex when the download of data through complex queries and with computation logic as well as complex formatting. Note: This effort includes of formation of excel / PDF with data retrieved
8 | Reports | The report is considered as Simple when the report has been generated based on simple query criteria of less than 2 input fields. The report is considered as Medium when the report has been generated based on query criteria of more than 2 input fields with computation logics. The report is considered as Complex when the report has been generated based on complex query criteria of more than 2 input fields with complex computation logics. Also this kind of report should have break wise report or hierarchy reports with complex formatting in presentation layer. Note: This effort includes end to end development of report development.
9 | Business Logic Operations | The operation is considered as Simple when it has 1 functional method (not java method) with the simple logics & validations The operation is considered as Medium when it has more than 1 functional method (not java method) & less than 3 methods with the medium complexity logics & validations The operation is considered as Complex when it has more than 3 functional methods (not java method) with the complex logics & validations
10 | Database Design Creation | The database design is considered as Simple when involes creation of less than 3 tables. The database design is considered as Medium when the design comparises creation of 3- 6 tables. The database design is considered as Complex when the design comparise creation of 6+ tables
11 | Theme/Layout design | The theme/layout design is considered as Simple when the portal consists of normal theme integration The theme/layout design is considered as Medium when the portal consists of more than 6 multiple theme integration. The theme/layout design is considered as Complex when the portal consists of more than 10 multiple theme integration.
12 | LARA Integration | The LARA Integration is considered as Simple when the solution consists of at least 2 screens to integrate with LARA Mirror DB The LARA Integration is considered as Medium when the solution consists of at least 3-5 screens to integrate with LARA Mirror DB The LARA Integration is considered as Complex when the solution consists of more than 5 screens to integrate with LARA Mirror DB
13 | Dashboards | The Dashboards is considered as Simple when the solution consists of at least 2 dashboards in the application The Dashboards is considered as Medium when the solution consists of at least 3-5 dashboards in the application The Dashboards is considered as Complex when the solution consists of more than 5 dashboards in the application
Web Services
14 | Web Services | The web services is considered as Simple when the solution consists of 1 web services The web services is considered as Medium when the solution consists of 2-4 web services The web services is considered as Complex when the solution consists of 4-8 web services
15 | Administration Settings | The Administration Settings is considered as Simple when the solution consists of at least 2 settings screens in the application The Administration Settings is considered as Medium when the solution consists of at least 3-5 settings screens in the application The Administration Settings is considered as Complex when the solution consists of more than 5 settings screens in the application

## Total Project Efforts - Summary
Estimation for SDLC Phases
| Summary Sheet |  |  | Estimated LOC
| Scope Area | Total Efforts (in Hrs) | Effort in Days (@ 8hrs) | Estimated LOC Added
| Requirement Analysis | 63.8571 | 7.9821 | Estimated LOC Modified
| Planning | 21.2857 | 2.6607 | Estimated LOC Deleted
| Design | 21.2857 | 2.6607 | Total No Of LOC underwent change | 0
| Coding, Unit Testing and UAT Support | 149 | 18.625
| System Testing and UAT Support | 85.1429 | 10.6429
| SDLC Development Efforts | 340.5714 | 42.5714
| Post Production Support | 42.5714 | 5.3214
| Project Management | 34.0571 | 4.2571
| Total Project Efforts | 417.2 | 52.15
| Project Classification | Major
Note: | This sheet would be a Summary for calculating the SDLC hours
Please read the ReadMe sheet on each program units, before counting the same.
Please fill up the Project Effort worksheet as per the information on hand.
Kindly split the requirements to each flow wise for better clarity and estimation accuracy
Benchmarks worksheet is the place where the efforts for every activity are determined as per industry standards

## Project Effort
Computation of Project Effort based on the understanding
Note 1 : Please don’t delete or add any rows in between in below table
S.No | Operations / Program Units | Input Screens |  |  | Search Criteria - Retrieves |  |  | Display Screens |  |  | Processing Logics |  |  | Batch Job |  |  | Uploads |  |  | Downloads |  |  | Reports |  |  | Business Logic Operations |  |  | Database Design |  |  | Theme/Layout design |  |  | LARA Integration |  |  | Dashboards |  |  | Web Services |  |  | Administration Settings |  |  | Total Efforts
|  | S | M | C | S | M | C | S | M | C | S | M | C | S | M | C | S | M | C | S | M | C | S | M | C | S | M | C | S | M | C | S | M | C | S | M | C | S | M | C | S | M | C | S | M | C | S | M | C
1 | Indexer Form - Enable the copy & paste option in this date and time input box | [9 empty] | 1 | [35 empty] | 2 | 0 | 0
2 | Indexer form - Default fileds setting | [9 empty] | 1 | [35 empty] | 2 | 0 | 0
3 | UPF-User clicks on the “Unique key” the request must be assigned and auto saved in the name of that particular user | [10 empty] | 1 | [34 empty] | 0 | 5 | 0
4 | UPF-Edit user of any request by admin and publishing time starts again | [10 empty] | 1 | [34 empty] | 0 | 5 | 0
5 | UPF-Status shown as per the Queue | [10 empty] | 1 | [34 empty] | 0 | 5 | 0
6 | UPF-Reefer Container request should add Commodity on demand by any user. There should be the button to access the Commodity Master | [6 empty] | 1 |  |  |  | 1 | [34 empty] | 4 | 5 | 0
7 | UPF-ISR Initiated free text field for RFI Pending In |  | 1 |  |  |  |  | 1 | [38 empty] | 4 | 8 | 0
8 | Publish Queue - COR TAT is 3hrs and should comes under red category | [7 empty] | 1 | [37 empty] | 0 | 8 | 0
9 | Publish Queue - DESREGARD status record should moved to Completed Queue | 1 | [44 empty] | 4 | 0 | 0
10 | Publish Queue-Excel Download | [18 empty] | 1 | [26 empty] | 4 | 0 | 0
11 | APF-Auditor clicks on the “Unique key” the request must be assigned and auto saved in the name of that particular auditor | [9 empty] | 1 | [35 empty] | 2 | 0 | 0
12 | APF - Edit user of any request by admin and auditing time starts again | [10 empty] | 1 | [34 empty] | 0 | 5 | 0
13 | APF-Status shown as per the Queue | [9 empty] | 1 | [35 empty] | 2 | 0 | 0
14 | APF-Modes, Lanes and Inland fields | [9 empty] | 1 | [35 empty] | 2 | 0 | 0
15 | APF-ISR Initiated free text field for RFI Pending In | [9 empty] | 1 | [35 empty] | 2 | 0 | 0
16 | APF-Pending Out Datetime Field with validation | [9 empty] | 1 | [35 empty] | 2 | 0 | 0
17 | Audit Queue-Excel Download | [18 empty] | 1 | [26 empty] | 4 | 0 | 0
18 | Audit Queue - DESREGARD status record should moved to Completed Queue | [9 empty] | 1 | [35 empty] | 2 | 0 | 0
19 | Completed queue - All DONE and DESREGARD status record should see in Completed Queue | [9 empty] | 1 | [35 empty] | 2 | 0 | 0
20 | Completed Queue-Excel Download | [18 empty] | 1 | [26 empty] | 4 | 0 | 0
21 | Daily Report-DRY Container | [22 empty] | 1 | [22 empty] | 0 | 27 | 0
22 | Daily Report-REEFER Container | [21 empty] | 1 | [23 empty] | 12 | 0 | 0
23 | Every Report-Should include DISREGARD in every section | [22 empty] | 1 | [22 empty] | 0 | 27 | 0
24 | [46 empty] | 0 | 0 | 0
25 | [46 empty] | 0 | 0 | 0
26 | [46 empty] | 0 | 0 | 0
27 | [46 empty] | 0 | 0 | 0
| Total Efforts (CUT) | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 95 | 0
| Total CUT Efforts (In hours) |  |  |  | 149
Yes
No
Note on C8: You can enter the program Units from here

## Benchmarks
Benchmarks
1 | Application related effort complexities (In hours) for Coding & Unit testing
| S.No | Program Units | Simple | Medium | Complex
| 1 | Input Screens | 4 | 8 | 20
| 2 | Search Criteria - Retrieves | 12 | 20 | 30
| 3 | Display Screens | 4 | 8 | 20
| 4 | Processing Logic | 2 | 5 | 9
| 5 | Batch job | 8 | 15 | 30
| 6 | Upload | 20 | 30 | 40
| 7 | Downloads (Excel / PDF) | 4 | 8 | 20
| 8 | Reports | 12 | 27 | 48
| 9 | Business Process Operations | 27 | 48 | 90
| 10 | Database Design creation | 16 | 24 | 40
| 11 | Theme/Layout design | 16 | 24 | 40
| 12 | LARA Integration | 8 | 16 | 24
| 13 | Dashboards | 24 | 32 | 40
| 14 | Web Services | 8 | 16 | 24
| 15 | Administration Settings | 24 | 40 | 64
2 | Phase wise effort distribution (In %)
| S.No | Phases | Weightage Distribution
| 1 | Requirement Analysis | 15%
| 2 | Planning | 5%
| 3 | Design | 5%
| 4 | Build / Coding and UAT support | 35%
| 5 | System Testing and UAT support | 20%
| 6 | Project Management | 10%
| 7 | Post Production Support | 10%