## Meeting Notes
Document ID |  | SSC/IND/FOR/GEN/046 | Document Classification | Internal
Meeting Date |  | Tuesday 26th July 2016 @ 5:30 pm, Coreteam Desk | Next meeting
Prepared By |  | PANDIAN Muneeswaran
Attendees: |  | GHADIGAONKAR Devendra, PADWALKAR Vinod , Sunil Wananje, PANDIAN Muneeswaran
Not Present |  | ALAUDAYAN Balachander
Sl.No | Agenda/Topic | Minutes
1 | F2F SQ Creation Initial Discussion | 1. High level business flow of F2F SQ Creation 2. Comparision study with Guideline Quoting 3. Effort level estimation for added requirements compare with Guideline Quoting 4. LARA intercface 5. Pricer reminder management & Spot rate 6. Reports

## Meeting Action Items
Sl.No | Action Items | Responsible Person / Team | Remarks | Dates |  |  | Status
|  |  |  | Action Open Date | Target Closure Date | Actual Closure Date
1 | Requested LARA screenshots from business team | Commercial Support - Service Contract Mgnt | Via email | 2016-07-26 | 2016-07-27 | 2016-07-27 | Closed
2 | Project plan | Development Team | Requested | 2016-07-27 | 2016-08-01 |  | Open
SSC/IND/FOR/GEN/046 |  |  | Internal |  |  |  | V1.0