## Cover Sheet
Project Name |  | CIRA - F2F SQ Creation |  |  |  |  | Note: Standardized version numbering convention: Drafts – (Before approval signature) 0.# 0.#+1 0.#+2 Published – (Once there is an approval on the document) 1.0 1.# 1.#+1
Business Unit |  | IT - Application Development
Project Manager |  | Ananthakrishnan ANBALAGAN
Created By |  | Sunil Wananje
Created Date |  | 2016-10-26
Reviewer |  | Hemanth Kumar
Reviewed Date |  | 2016-11-08
Approver |  | Venkatasubramanian NARASIMHAN
Approved Date
Version # |  | 1
Document History |  |  | Document Classification | Internal |  | Document ID |  | SSC/IND/FOR/GEN/050
[6 empty] | Version |  | V 1.1
Version No. | Nature of modification |  |  | Effective date | Modified By |  | Approved By | Approved Date
1 | Initial Baseline |  |  | 2016-10-27 | Sunil Wananje |  | Hemanth Kumar | 2016-11-08
1.1 | Code review update |  |  | 2017-01-10 | Chandrabose

## Review Tracker
Review Tracker
S.No | Lifecycle | Review Document Type | Author | Reviewer | Review Defect Description | Severity | Cause | Phase Detection | Defect Origin | Status | Date of review | Date of completion | Remarks
1 | Development | Coding | Sunil Wananje | K Chandra Bose | Large line of coding has been divided into small function for better understanding with proper commented with the appropirate name of functions. | Minor | Oversight | Coding | Coding | Closed | 2016-09-28 | 2016-09-28
2 | Development | Design | Sunil Wananje | K Chandra Bose | Make reusable code, Add proper comments to each module | Minor | Oversight | Coding | Design | Closed | 2016-09-29 | 2016-09-30
3 | Development | Design | Sunil Wananje | K Chandra Bose | Databse Query should be more optimize for publishing queue and auditing queue, Use add proper indexing to table getting better performance for search and filter data | Minor | Oversight | Coding | Design | Closed | 2016-10-01 | 2016-10-03
4 | Testing | UTC | Sunil Wananje | P Muneeswaran | Urgent booking not in red color | Minor | Changes in requirements | Unit testing | Unit testing | Closed | 2016-09-19 | 2016-09-21
5 | Testing | UTC | Sunil Wananje | P Muneeswaran | Enable calendar to add Holiday list | Minor | Oversight | Unit testing | Unit testing | Closed | 2016-09-22 | 2016-09-26
6 | Testing | UTC | Sunil Wananje | P Muneeswaran | Change the TAT format to HH:MM | Minor | Changes in requirements | Unit testing | Unit testing | Closed | 2016-09-22 | 2016-09-26
7 | Testing | UTC | Sunil Wananje | P Muneeswaran | OOT remarks not mandatory | Minor | Oversight | Unit testing | Unit testing | Closed | 2016-09-22 | 2016-09-26
8 | Testing | UTC | Sunil Wananje | P Muneeswaran | Mark the mandatory fields as '*' | Minor | Oversight | Unit testing | Unit testing | Closed | 2016-09-27 | 2016-09-29
9 | Testing | FTC | Sunil Wananje | P Muneeswaran | Unable to tick the OOT checkbox | Minor | Oversight | System Testing | System Testing | Closed | 2016-10-21 | 2016-10-24
10 | Testing | FTC | Sunil Wananje | P Muneeswaran | Disable Generate Request button in Indexer | Minor | Changes in requirements | System Testing | System Testing | Closed | 2016-10-21 | 2016-10-24
11 | Testing | FTC | Sunil Wananje | P Muneeswaran | Incorrect RFI raised time captured | Minor | Oversight | System Testing | System Testing | Closed | 2016-10-21 | 2016-10-24
12 | Testing | FTC | Sunil Wananje | P Muneeswaran | RFI raised date captured, without raising the RFI | Minor | Oversight | System Testing | System Testing | Closed | 2016-10-21 | 2016-10-24
13 | Testing | FTC | Sunil Wananje | P Muneeswaran | RFI details not mandatory while 'Send to Audit' | Minor | Oversight | System Test case review | System Testing | Closed | 2016-10-21 | 2016-10-24
14 | Testing | FTC | Sunil Wananje | P Muneeswaran | Once index done move the cursor to mail receiving box | Minor | Oversight | System Test case review | System Testing | Closed | 2016-10-21 | 2016-10-24
15 | Code Review | Coding | Sunil Wananje | Chandra Bose | Last enhancement changes has followed as per the framework standards . Coding has been commented with the appropirate name for the better understanding.
[14 empty] | Lifecycle |  |  | Phase Origin | Status
[14 empty] | Dev | Misunderstanding | Incomplete test cases | Project plan | Open | SOP
[14 empty] | Testing | Requirement not clear | No test data | User Requirement | Closed | Project charter
[14 empty] | Support | Suggestion | Inappropriate test data | Design-HLD | Not Resolvable | Test Plan
[15 empty] | Missed requirements | Incorrect expected behaviour | Design-LLD. | Not Reproducible | End User error
[15 empty] | Documentation error | Changes in requirements | Coding | Not Applicable | Configuration error
[15 empty] | Logic error | Misunderstanding of requirements | Code Review | Duplicate | Environmental error
[15 empty] | Design error | Missing requirements | Unit test case review | Deferred | Access failure
[15 empty] | Missed error handling | Oversight | Unit testing |  | Oversight
[15 empty] | GUI error |  | Integration test case review. |  | Suggestion
[15 empty] | Hardware interface error |  | Integration Testing
[15 empty] | Interface error |  | System Test case review
[15 empty] | Environment changes |  | System Testing
[15 empty] | Changed requirements |  | Regression Test cases
Regression Testing.
User Acceptance testing.
Post production
User Manual
Note on C8: Author Project Plan BRD Code Design Test case User Manual UAT Test case Test Results